## Sheet1
Category | Issue | Notes
General Issues & Fixes
FAQs Update | Change and update FAQs as required
Login Issues | Sign in with Gmail and other methods not working | Needs to be fixed
| Email verification issue | Page gets distorted when clicking 'Verify with Email'
Post Login Requirements
Banner Ad | A banner ad should be provided
Banner ad should also be displayed on the recruiter side
Task Board | Currently empty; clarify what should be displayed
Profile Completion | Same issues as recruiter
Payment Method | Should not be saved; only required when posting a job
Data Saving | No information is being saved
Company Details | Pull company details by AAL
Post Job | Issues found in job posting process
Change image as discussed
AI Writing | Write with AI not working
Interview Process | Add various steps in the selection process
Interview with founders/management
Reward System | Enter reward amount per successful closure
Add note: Reward amount is the commission payable on successful hiring. Released after 60 days.
Show recruiters that topping up their wallet can lead to faster closures
Jobs Section | Showing 'Hired Candidate' automatically under jobs
Recruiter ID | Recruiter ID is showing unnecessarily
Emails | Clarify communication flow on all levels
Closing Jobs | How to close an active job?
Dashboard | Buttons for recruiters, candidates, etc. not working
Frontend Issues & Fixes
Login | Recruit on Your Terms - Word Capitalization
Remove 'Only' and keep 'Top Companies' on Homepage
Add 'For Companies' and 'For Recruiters' on the top bar
Change '90% Satisfaction' to '90% Fill Rate'
Images for 'Our Recruiting Verticals' will be shared
Scrolling over an image overlaps text in some cases
In 'Why Choose Shiftz' - Ensure first letter capitalization
Remove Testimonials section
Quick Links are not working
Social Media Links are not working
Add all policies on Homepage from old site
Contact Us page is missing
Add 'About Us' with write-up and pictures
Remove 'Choose from the Best Companies' section
In Testimonials, add images or remove image circle
FAQs updated as per shared details
'Get Started' button takes a while to load
Change Email option needed
Sign up with Google and LinkedIn not working
Post Verification Email - Welcome Emailer
Credit That Work - Remove 'Simply' and Add 'Connect with Leading Employers Today!'
Current Credits (100 Credits) - Not Clickable; Clarify Purpose
Buy Credit Section - Change Terms and Plans as Shared
Profile Completion | Professional Details Section - Pencil Icon for Edit, Make Standardized
Industries - Allow Multiple Selection
Key Roles - Allow Multiple Selection
After Filling Professional Details, Yes/No Section Disappears
LinkedIn Profile Integration in 'About You'
Certifications Not Getting Saved
Unable to Edit Photo and Other Details
Even After Filling, Profile Shows Only 30% Completed
Main Page | Choose Industry - Not All Industries Showing in Dropdown